2. Table of Contents

Pages

- Proposal Cover Page

- Table of Contents

- Project Summary Form

- Project Description…………………………………………1-12

- Reference…………………………………………………...12

- Appendix to Project Description……………………………13

- Key Personal………………………………………………..14

- Collaborative Arrangements (Letters of Support)…………15-25

- Conflict of Interest List……………………………………..26

- Budget………………………………………………………27

- Budget narrative…………………………………………….28-29

- Matching…………………………………………………….30

- Current and Pending Support……………………………….30

- Assurance Statement………………………………………..31

- Compliance with the

National Environmental Policy Act…………………………32

- Page B, Proposal Cover Page, Personal Data

on Project Director…………………………………………..33

Executive Summary

Children growing up in Birmingham currently face an epidemic.  A recent finding in the Youth Risk Behavior Survey stated that youth in Birmingham eat fewer fresh vegetables and have a higher rate of early childhood obesity than almost any other city.  In response to this, Jones Valley Urban Farm is creating the Growing Urban Food Connections program (GUFC). In conjunction with converting an entire city block in downtown Birmingham into a model urban farm, GUFCP will enable JVUF to become a permanent part of the fabric of downtown Birmingham and expand our current programs.  The three main areas we will address are: high school agri-science education, nutritional education, and community food security.

This program will create direct linkages between urban food production and low-income households in Birmingham’s ‘central city’ community.  The involvement of these residents will revolve around the creation of the Community Food Advisory Committee (CFAC) and a sliding-scale Community Supported Agriculture project (CSA).  As a result of GUFC, these households will have access to high quality healthy food, new economic opportunities, and an empowered sense of community involvement.

Birmingham is fertile ground for food security program and has not received the attention it needs to address the issues. JVUF has grown over the past 4 years and is now poised to blossom into a truly community-based responsive project, something Birmingham desperately wants and needs.  With the assistance of the GUFC, JVUF will be able to provide long-term food security solutions to Birmingham’s ‘central city.’

4. Project Description

- Community to Be Served and the Needs to Be Addressed (Statement of Need)

The community we are targeting is actually a relatively ‘new’ neighborhood.  Unlike the other neighborhoods JVUF has worked with in the past - Southside neighborhood or the East Avondale neighborhood of Birmingham that both have a long-time residents - the ‘central city’ community of Birmingham has recently undergone a radical transformation on two fronts.  The public housing community that has made up the core of ‘central city’ for the last 50 years (Metropolitan Gardens) has recently been transformed by a Hope VI grant.  This entailed tearing down the old public housing and rebuilding a ‘mixed-income’ community.  In addition, the once ‘vacant’ warehouse district in downtown has recently been converted into a ‘loft’ residential community.

The combination of these two changes in the demographic make-up of ‘Central City’ offers a number of exciting challenges and opportunities.  The foremost challenge is to identify the needs correctly for a community of people that have not lived in the area of long.  The opportunity is to provide a unique ‘mixing’ ground for one of Birmingham’s first truly ‘integrated’ neighborhoods.  From a food security perspective, this is particularly exciting.  While some residents will have enough resources to provide for their needs adequately, their neighbors may not.  It is our primary goal as to make sure all these residents know how and where to get food that is fresh, healthy, and affordable.

Alabama’s Health Challenges   As of 2005 Alabama ranks 45th According to the United Health Foundation America’s Health Rankings in national health status due to the high rates of obesity (28.4) and diabetes (8.7%), increasing rates of children in poverty, and high premature death rate (9,960 years before age 75 lost per 100,000). In the past year in Alabama the per capita public health spending increased from $147 to $159 per person while the percentage of children in poverty increased also increased from 22.3 percent to 24. Since 1990, the prevalence of obesity has more than doubled, going from 12.3 percent to the current 28.4%.

Focus on City of Birmingham, Alabama

Birmingham City	         Alabama		U.S.

Percent African-American			73.5			21.2		16.1

Percent	 on Disability				27.6			23.2		19.3

Percent Below Poverty

Families 				20.9			12.5		9.2

Individuals 				24.7			16.1		12.4

Children <18 years		           35.4 			21.2		16.1

Over a third of Birmingham city children live in families below the poverty level. Younger generations, especially among the lower income communities have been shown to be becoming increasingly reliant on lesser nutritious convenience and fast foods. In conjunction with the tendency for Alabama children to eat the fewest fruits and vegetables of other states surveyed, Alabama children living in poverty are at even greater risk for health complications that can be easily prevented by dietary improvements and educational intervention.  Now more than ever nutritional education is needed to help Birmingham youth stop and reverse these negative health trends.  Gardening activities also provide children with much needed physical activity.

Educational Programs Promote Long-term Program Sustainability Targeting youth with educational programs and school field trips helps to build interest and awareness in the economic and nutritional possibilities of improving food security through local food production.  Providing opportunities for local high school students to work and participate in community garden programs further establishes a tradition of community-based food production and entrepreneurship.   Long-term, self-driven program sustainability depends on maintaining community involvement and continuing to make the community garden accessible to local, school-age children.

The Community – ‘Central city neighborhood’ The 12-block downtown development includes more than the 637 units of mixed-income housing.  Sixty percent of the residences fall under the affordable housing program. Park Place and other Hope VI projects look to create mixed-use, diverse, vibrant neighborhoods conducive to community-driven projects such as the Gardens of Park Place.  As of this grant writing the neighborhood is currently continuing to develop and take in residents.  The demographic of the immediate area is expected to resemble that of Birmingham city (see table) primarily composed of African American low to moderate-income families and seniors.  A greater percentage than at the State or National level of children living at or below the poverty level is also expected for the neighborhood.

- The Organizations Involved in the Project

Jones Valley Urban Farm (JVUF)

JVUF is a non-profit community-based project in its fourth year of operation.  The project seeks to improve the quality of life for residents of Birmingham in three ways: urban restoration, organic food production, and environmental education.  These three objectives have been accomplished by converting three urban properties into organic production farms, creating an agri-science course for local high school students, and helping to start the Community Food Security Coalition of Jefferson County.  JVUF’s education program, called the Arts and Science of Agriculture Program (ASAP), was partially funded by a USDA Secondary Agricultural Educations grant.  It was implemented in 2003 and the grant was completed in 2005.  ASAP is continuing to run both summer and academic year programs.

JVUF is now in a position to expand by taking over an entire city block and developing a model demonstration urban farm in the heart of a Hope VI neighborhood.  This project, called The Gardens of Park Place, will house all future urban gardening and education programs for JVUF, including The Growing Urban Food Connections Project (GUFCP).  This innovative new project will be modeled on our past success of collaboration and low-income residents will help develop each objective and their input throughout the project will guide us in our future goals.

All of these accomplishments have linked urban households directly with their food system, either by providing food directly, educating urban youth about agri-science, or expanding capacity for residents to produce their own food.  The key to these successes has been the extensive collaborations JVUF developed.

The Alabama School of Fine Arts (ASFA), a public magnet school located in Birmingham’s Central City. ASFA provides specific training in the arts and sciences to a wide range of students from diverse ethic and economic backgrounds.  ASFA and JVUF developed a collaboration in 2003 to provide an accredited science course (ASAP) for high school juniors and seniors.  We have run the program every summer and also developed an academic year program by developing a school garden on the ASFA campus.  ASAP will continue as both a summer course and academic year course.

The YMCA, located one block from JVUF’s new urban farm (the Gardens of Park Place), we are in a unique position to develop collaborations with their ‘after-school’ programs as well as summer camps.  The YMCA recently underwent a Five million dollar retrofit that includes a ‘teaching’ kitchen.  The Y has agreed to develop collaborative programs centered on teaching students about food production at the Gardens of Park Place and continuing with culinary education at the YMCA (see Seed 2 Plate).

The Community Food Security Coalition of Jefferson County (CFSCJC), a response to the recognition that there are ‘food insecure’ communities in Birmingham.  This coalition comprises a dozen NGO’s and faith-based organizations, such as Magic City Harvest, Community Kitchens, Greater Birmingham Ministries, Independent Presbyterian Church, Urban Ministries, and many others.  The goal of the coalition is to promote access for all community residents to a safe, culturally acceptable, nutritionally adequate diet through sustainable food system that maximizes community self-reliance and social justice. The Coalition will work closely with the JVUF to develop a Community Food Assessment Committee and help implementing a Central City community food assessment.

In-Town, a collaborative response to the Hope VI redevelopment of the Metropolitan Gardens in downtown Birmingham, adjacent to JVUF’s Gardens of Park Place.  The organization will coordinate activities between the various NGO’s involved with the Hope VI project (called Park Place.)  In-town will assist JVUF in developing the Community Food Advisory Committee and act as a liaison between the management of Park Place and JVUF.

Central City Neighborhood Association, the neighborhood association that comprises ‘downtown’ Birmingham.  These neighbors include the new ‘Loft’ district, the new Park Place mixed-income community, and the ‘financial’ district.  The neighborhood president, Toni Leeth, will be a critical link between the low-income households in the Central City and the Community Food Advisory Committee.

The James 1 Rushton Foundation (J1RF), own the city block that JVUF will develop into the Gardens of Park Place.  J1RF developed a successful community garden 12 years ago for low-income residents of the community.  However, when the Hope VI project tore down the old Metropolitan Public Housing Neighborhood, J1RF developed collaboration with JVUF to utilize the vacant community garden.  After 3 years of JVUF farming the former community garden, JVUF proposed the idea for the Gardens of Park Place.  J1RF agreed to the idea of converting the entire city block into an urban farm and are currently providing funding for its implementation.

The Culinard Institute, a local college providing job-training skills in the culinary arts.  JVUF began collaboration in 2003 with ASAP students visiting the ‘teaching’ kitchens and learning to prepare the produce they had grown.  This idea grew in the Seed 2 Plate fieldtrip, where the Culinard brings out ‘mobile’ kitchens for students to cook the produce they helped grow on-site.

The University of Alabama at Birmingham (UAB), Department of Nutrition Sciences, Dr. Amanda Brown works with the Community Food Security Coalition of Jefferson County and agreed to supply Dietetic Interns for the Seed 2 Plate fieldtrip.  These interns will help teach the students how to transfer what they learn on the fieldtrip with their daily lives.

Heifer International, Gus Heard Hughes, the Southeast Field Representative, has worked closely with JVUF over the last four years, assisting the project with technical advice, funds for internships, and we are currently developing a 3 year nutrition-based project.  Heifer is also a partner in the Community Food Security Coalition of Jefferson County.

- Project Goals and Objectives

The three primary objectives of the Growing Urban Food Connections program revolve around making sure all residents in the ‘Central City’ community of Birmingham understand the importance of and have access to healthy food.

1) Agri-science education

Working in conjunction with the Alabama School of Fine Arts and the Birmingham city schools, JVUF will expand our innovative Arts and Science of Agriculture Program (ASAP).  This high school agri-science course teaches inner-city youth about sustainable food production and their connection to the food system.  We will expand this course to include students from other inner-city schools and offer course scholarships for low-income participants.  There will be a total of 80 students participating in ASAP over the two year project duration, with at least one-quarter representing low-income households.  This will be coordinated with the schools administration.

In addition to expanding the number of students participating in ASAP each summer, JVUF will provide the ASAP curriculum to other schools through a series of Training the Trainers course.  Finally, working in conjunction with various national urban agriculture organizations, JVUF will co-host a Sustainable Agriculture Educators Conference for Secondary Schools.  This conference will provide different organizations the opportunity to network, share curricula, and discover what is lacking in the current education system for high school agri-science courses.

2) Nutritional Education

JVUF will work with the Culinard Institute of Virginia College to develop various nutrition education programs.  These programs will include the Seed 2 Plate fieldtrip for elementary and secondary inner-city schools.  100 students per month will come to the urban farm and participate in growing food, harvesting produce, and preparing the food with a mobile kitchen unit. The total number of students participating will be 1600 over the two year grant period.

JVUF will also seek new ways to connect inner-city children, their parents, and the food system.  We will use the Jefferson County Food Assessment as an opportunity to connect with food-insecure communities to determine what programs would be of most value to them and most likely to lead to long-term behavioral changes, such as Food to School programs.  JVUF is currently working with Heifer International, a collaborator on previous JVUF projects, to explore partnerships around these programs.

3)Food Security

Focusing on the ‘Central City’ neighborhood adjacent to our new demonstration urban farm, JVUF will develop a Community Food Advisory Council to assist with developing innovative responses to the needs of this neighborhood.  The primary project will be developing a sliding-sale Community Supported Agriculture project (CSA).  This will supply local households with fresh organic produce at a price that they can afford.  In the first year, 25 households will participate.  The second year 50 shares will be offered and in the following years, JVUF will offer 100 shares.  Possible additional projects included an Inner-city Youth After-market Product program, with JVUF hiring 5 low-income youth each year to grow, process, and market organic pesto, preserves, and salsa.  The total number of youths involved over the grant period will be 10.

JVUF is also currently helping to develop The Community Food Security Coalition of Jefferson County (CFSCJC). This coalition is developing the capacity for a county wide food security assessment in the next year.  JVUF’s primary role in the coalition will be to respond to the needs of communities stated in the assessment with regards to developing new community gardens, farmers markets, and entrepreneurial urban agricultural projects.

- Activities to Achieve the Goals

1)Agri-Science

*GUFC will provide JVUF an opportunity to expand a successful existing program to meet the needs of low-income residents in Birmingham’s ‘Central City.’  In 2003, JVUF created this collaborative education program with a ‘Central City’ public magnet school called the Alabama School of Fine Arts (ASFA). It’s an accredited experiential education course called the Arts and Science of Agriculture (ASAP) and it's offered for 2 semesters each summer, with each semester lasting 4 weeks. The students come out to the urban farm 5 days a week for 5 hours and help with all aspects of production, such as sowing seeds, weeding, and harvesting. Twice a week, they have lectures on various agroecology subjects, take field trips, and present research projects.

*In 2004, ASFA and JVUF expanded the education class to include an academic year component, with 2 semesters each year in fall and spring. The course is based around the school garden JVUF helped develop and offers ASFA students an opportunity to receive a science credit for this experiential course at their own school.

*JVUF will expand both the summer and academic year ASAP course in conjunction with the Alabama School of Fine Arts and the City schools of Birmingham.  This High School agri-science course teaches inner-city youth about sustainable food production and their connection to the food system.  We will expand this course to include students from all ‘central city’ schools.  Non –‘central city’ students will be charges $250 per semester for ASAP while all ‘central city’ students will receive a scholarship.  This arraignment allows JVUF to move towards creating a ‘self-sustaining’ program while still providing education programs for low-income students.

*JVUF will provide the ASAP curriculum to other schools through a series of Training the Trainers course.

*Working in conjunction with various national urban agriculture organizations, such as Georgia Organics, Boston’s Food Project, and Life Lab.  JVUF will co-host a Sustainable Agriculture Educators Conference for Secondary Schools.  This conference will provide different organizations the opportunity to network, share curricula, and discover what is lacking in the current education system for high school agri-science courses.

2) Nutritional Education

*Recognizing the need to address the critical health issues facing the ‘Central City’ low-income households, JVUF will work with the Culinard Institute and the YMCA to develop nutrition education programs.  These will include the Seed 2 Plate fieldtrip for elementary and secondary inner-city schools during both the academic year and with YMCA’s summer camp.

*The basic component of the project will be a half-day nutritional experiential field-trip offered to Elementary and Middle Schools in the Greater Birmingham Area.   Seed 2 Plate will be offered from August through May and class size will be restricted to 20 students a day to ensure a true experiential experience for each participant.

*Students will arrive at JVUF at 9:30 a.m.  JVUF staff will provide students with an introduction to the farm; including our history, safety-guidelines, and the program objectives.  From 10:00 to 12:00 students will break into small groups and rotate through a series of stations, each focusing on aspect of organic food production.  These stations will include soil preparation, seed propagation, compost production, weed and pest management, and harvesting.  Students will learn about each subject while actually participating in the activity.  Once each group has moved through all the stations, students will take the harvested produce to the ‘mobile kitchen’ provided by the Culinard.

*From 12:00 to 12:30, staff from the Culinard will work with students to prepare the produce and cook lunch.  Student will again learn about the Culinary Arts while actually assisting the chef.  At 12:30, the students will help set the tables at the farm for a feast and serve their own food.  While eating lunch, a nutritionist from UAB’s Dieticians program will provide fun interactive ways for the students to see why the food they are eating is different from the food they usually eat for lunch.  This will include information on the benefits of eating fresh organic produce, the benefits of eating ‘lightly’ cooked or raw food, and finally on how to translate these benefits back to their home.

*Students will leave at 1:00 with publications about good eating habits, contact information for their parents to get involved with the farm or community gardens in their neighborhood, and seedlings to start their own garden.  In addition, parents will be given $10 produce vouchers that they can reimburse for JVUF produce at either the farmers market or the farm stand.  Finally, students will be asked to keep a food journal for the week following the fieldtrip.  Students will document what they eat at each meal and encouraged to submit their journal for a contest.  The most creative journal that shows good eating habits will earn the student a JVUF t-shirt.

*Non-‘central city’ schools will be charged $10 per student to offset the cost of the fieldtrip and pay for lunch supplies.  JVUF will offer fieldtrip subsidies as well as transportation assistances to all ‘central-city’ schools.   By charging a minimal fee for the fieldtrip, JVUF will be able to create a self-sufficient program by the second year of operation.

3) Food Security

*The key to successfully reducing food insecurity in Birmingham’s ‘Central City’ is knowing what the real issues are.  JVUF will seek this information through the Community Food Advisory Committee.  This group is being developed currently and will comprise a wide cross-section of the community, such as neighborhood association representatives, church groups, low-income residents, business owners, and public officials.  This committee will be an avenue to direct community participation by encouraging representatives to get more people involved and learn what resources the community possesses to address their own needs.

*The purpose of the CFAC is to provide direct involvement with all current JVUF programs and, more importantly, to direct all future programs.  This will be implemented by the CFAC serving as a potential pool for JVUF’s Board of Directors.  By the end of 2007, one quarter of the Board will be comprised of CFAC members.

*JVUF is also currently helping to develop The Food Security Coalition of Jefferson County (FSCJC). This coalition is developing the capacity for a county wide food security assessment in the next year.  JVUF’s primary role in the coalition will be to respond to the needs of communities stated in the assessment with regards to developing new community gardens, farmers markets, and entrepreneurial urban agricultural projects.  With the involvement of the CFAC, a community food security assessment will be planned for Birmingham’s ‘Central City.’  CFAC will provide the direct linkages to the low-income households in the area and help develop culturally appropriate means for assessing community needs.  Possible projects include developing a ‘Youth Entrepreneurial Business’ program.

*With an assessment complete, JVUF will be ready to respond to whatever strategies the CFSCJC and CFAC see as most critical.  Possible program include Youth Entrepreneurial Business Opportunities.  This would be an inner-city Youth After-market Product program, with JVUF hiring low-income youth to grow, process, and market organic pesto, preserves, and salsa.  We will seek the advice of various successful programs around the country to best plan and implement this program.

*In addition to providing these ‘soft’ programs for addressing ‘central city’ food security, JVUF will also develop a Community Supported Agriculture program with a sliding-fee to allow low-income residents access to the fresh organic produce grown at the Gardens of Park Place.  The CSA will start in the spring of 2007 by offering 25 ‘central city’ households the opportunity to pay $500 in exchange for a box of what ever’s fresh on the farm for 20 weeks.  Working with the Housing Authority, and basing the program on Chicago’s Growing Power CSA ‘Market Basket’ program, we will develop a system for giving low-income households the ability to pay an affordable amount for their box of fresh vegetables.  In the second year, we will expand the CSA to 50 members and being asking ‘market’ rate households to donate money to pay for the subsidized CSA shares.  In the third year, we will grow the CSA to 100 members offer at least 25 of these to low-income households.  This program puts fresh sustainably produced food in the hands of the people that need it the most.

- Timeline

October 2006

*Hire an Education Coordinator and an Outreach Coordinator.

*Begin development of the Growing Urban Food Connections program.

*Meet with local representatives of the ‘Central City’ to create the Community Food Advisory Committee.

*Meet with local Birmingham city school representatives to explore opportunities for expanding the Arts and Science of Agriculture Program (ASAP) into all ‘Central City’ high schools.

*Continue development of the Gardens of Park Place, including soil improvements and building of the ‘Farm Center.’

January 2007

*Meet with Robby Melvin from the Culinard about implementing ‘Seed 2 Plate.’

*Advertise with ‘Central City’ elementary schools for Seed 2 Plate fieldtrip.

*Meet with the Community Food Advisory Committee to identify the potential ‘Youth Entrepreneurial Business Opportunities.’

*Recruit students from ‘Central City’ high schools for the summer ASAP course.

*Begin development of the Gardens of Park Place community garden, with direct involvement of the Community Food Advisory Committee.

March 2007

*Contact national organizations about planning a Secondary Agricultural Education Conference.

*Begin offering Seed 2 Plate fieldtrip to local schools.  Run 2 fieldtrips per week with 20 students per day.

*Hire 5 ‘Central City’ high school students for the ‘Youth Entrepreneurial Business’ program.

* Complete development of the Gardens of Park Place community garden and farm center.

*Plan for the Sliding-scale CSA.

May 2007

*Begin first semester of summer ASAP course with 15 ‘Central City’ high school students.

*Being summer Seed 2 Plate program with the YMCA summer camp participants.

*Being ‘Youth Entrepreneurial Business’ program by planting crops at the Gardens of Park Place for after-market products and planning marketing strategy.

*Offer garden plots to ‘Central City’ households, giving preference to low-income residents first.

*Begin delivering the CSA boxes to 25 local households.

Summer 2007

*Run 2nd semester of summer ASAP program with 15 more ‘Central City’ high school students.

*Continue Seed 2 Plate program with the YMCA.

*Begin collaboration between the Community Food Advisory Committee and the Community Food Security Coalition to implement a ‘Community Food Assessment’ in the Birmingham’s Central City.

Fall 2007

*Continue planning for the Secondary Agricultural Education Conference with organizations such as Georgia Organics, Life Lab, and the Food Project.

*Offer Fall semester of ASAP to local high school students at the Gardens of Park Place.

*Offer Seed 2 Plate fieldtrip to local elementary and middle schools.

*Complete first year of ‘Youth Entrepreneurial Business.’

*Implement Food Security Assessment in the ‘Central City’ with the Community Food Security Coalition of Jefferson County.

Winter 2008

*Continue organizing and host Secondary Agricultural Education Conference.

*Offer Spring semester of ASAP to local high school students.

*Continue Seed 2 Plate fieldtrip for local elementary and middle schools.

*Analyze Food Security Assessment with CFSCJC and the Community Food Advisory Committee.  Plan strategy for reducing food insecurity in the ‘Central City.’

Summer 2008

*Offer Summer ASAP course to local high school students

*Continue Seed 2 Plate collaboration with the YMCA’s summer program.

*Hire and implement 2nd year of ‘Youth Entrepreneurial Business.’

*Offer community garden plots to ‘Central City’ low-income residents.

*Again offer a sliding-scale CSA to 50 residents

Fall 2008

*Implement strategies developed by CFSCJC and CFAC for reducing food insecurity in Birmingham’s ‘Central City,’ such as starting a farmers market at the Gardens of Park Place, encouraging development of a local ‘green grocer,’ improving public transportation, or expanding community garden opportunities for low-income households.

*Provide Fall ASAP for local high school students.

*Provide Seed 2 Plate for local elementary and middle schools.

*Expand the ‘Youth Entrepreneurial Business’ by hiring a graduate of the program to coordinate program year-round.

2009

*Continue collaboration with national organizations for 2nd year of Secondary Agricultural Education Conference.

*Continue to offer ASAP to local high school students.

*Continue to offer Seed 2 Plate to local elementary and middle schools.

*Continue implementing strategies for reducing “Central City’ food insecurity at the direction of the CFSCJC and CFAC.

*Expand CSA to 100 households.

- Relation to Program Objectives

Our proposal meets the major goals of the Community Food Project in innovative and exciting ways.  The agri-science course (ASAP) develops linkages between low-income urban youth and the food system.  It provides students with direct experience of food production and the issues surrounding environmental sustainability.  The Secondary Agricultural Educators conference will bring national attention to this potential benefit to inner-city youth and develop more linkages between national programs.  The nutrient program, Seed 2 Plate, provides younger low-income youth with a similar experience.  Elementary and middle school students will get a unique, direct experience of how to grow food, how food is prepared, and ways to improve their diet.  Finally, the community food security component gives low-income adults an opportunity to either produce their own food (community gardens) or purchase healthy food at an affordable price(Sliding-scale CSA.)  In this way, all segments of Birmingham’s Central City community will have increased exposure and experience with the food system.

In addition, the Community Food Advisory Committee empowers low-income inner-city households to examine the major issues confronting their neighborhoods and participate in coming up with novel culturally-sensitive solutions.

- Evaluation

The evaluation for this program will be planned and implemented in collaboration with Jones Valley Urban Farm’s Board of Directors, the Community Food Advisory Committee, and the Non-profit Resource Center of Alabama’s consultant, Dalinda Thomas.  As members of NRCA for the last 4 years, JVUF has learned to trust the advice of this community resource and feels confident a fair and transparent evaluation will be implemented.

Mrs. Thomas will be hired at the start of the project and begin planning a series of quarterly meetings to discuss the development of an evaluation strategy, and to respond to issues as they appear. The evaluation will have two basic components; one quantitative and the other qualitative.

The quantitative evaluation will look at the projects stated goals and objectives, such as number of students participating in ASAP or Seed 2 Plate.

The qualitative evaluation will look at the impact these programs are having on the food security of the community.  We will have a unique opportunity to gather information by planning this phase of the evaluation with the Central City Community Food Assessment.  Working closely with all our partners, we will develop culturally- sensitive questions that can be revisited to find out the impacts of our programs.

- Self-Sustainability

Jones Valley Urban Farm has worked hard over the last four years to develop a program from scratch that would have a substantial and sustainable impact of the community.  This one-time grant will give JVUF the capacity to develop infrastructure and programs that will eventually fund themselves.

ASAP provides JVUF with two forms of self-sufficiency.  The first is a source of labor for agricultural production.  While we don’t ask students to perform anything the staff does not actively participate in, the influx of hands during harvest time can not be undervalued.  The second is a potential source of income.  As JVUF develops the ASAP curriculum, their will be opportunities to consult with other organizations and schools to develop similar programs, off-setting the salary of the Education Coordinator.  Additionally, the Secondary Agricultural Educators Conference will provide an opportunity to network with other organizations and find new potential markets for our curriculum.

Seed 2 Plate provides another potential source of self-sufficiency.  While the majority of fieldtrips will be offered to low-income Central City schools, other (non-Central City) may be also interested in participating.  These schools will be charged $10 per student, which is the average cost for fieldtrips in Birmingham.  These funds will help to substantially off-set to the Education Coordinators salary.

Finally, after the 2nd year the sliding-scale CSA will provide a large portion of the programs operating budget.  With ‘Market-rate’ CSA members subsidizing the ‘low-income’ members, JVUF could easily produce a $50,000 a year with the CSA alone

Budget Narrative

JVUF is seeking $145,000 over two years to assist in the implementation of these goals.  The funds will be used to partially pay JVUF’s Education Coordinators and Community Garden Coordinators salary for two year.  These staff positions will deliver JVUF’s education program and participate in the Food Security Coalition of Jefferson County.  The funding will also be used to help develop a demonstration community garden, farm stand at the Garden of Park Place, and host a national sustainable agriculture secondary educator’s conference.  Capital funding will be used to purchase a tractor and a walk-in cooler for the urban farm.  Finally, funding will be used to pay for an exterior evaluator of the project and to send participants to relevant trainings and conferences.

Matching funds for Growing Urban Food Connections will come from the James 1 Rushton Foundation.  $55,000 per year for two years will cover the Executive Directors salary and benefits.  $100,000.00 will cover the costs of developing our new urban farm location, called the Gardens of Park Place.  These funds will be used to build a farm center, with a classroom, greenhouse, and barn.  The funds will also be used to develop a community garden, orchard, and hardscaped pathways and parking.

Staff Positions

Education Coordinator –

$18,750 per year including benefits, such as medical insurance, life insurance, and workers comp.  75% of their time.

Community Outreach Coordinator –

$18,750 per year including benefits, such as medical insurance, life insurance, and workers comp.  75% of their time.

Direct Costs

Non-expendable Equipment

$15,000 tractor and spader (used).  Necessary to expand the CSA production

$10,000 walk-in cooler.  Necessary to store CSA produce.

$10,000 Community Garden tool shed and gazebo

Materials and Supplies

$5000 Compost and fertilizer for farm and community garden.  Hand tools for community garden.  Clerical supplies.

Publication Cost

$5000 for brochures, newsletters, and events.

Computer

$4000 for two lap-top computers and printer

Student Assistance/ Support

CSA Subsidy

$6000 for off-setting cost of low-income members in first two years.  After two years, CSA will have expanded to 100 members and off-set the subsidy.

Secondary Agricultural Educators Conference

$7,000 for hosting the conference at the Gardens of Park Place.   These funds will used to cover the following: $2000 for organizational administrative costs, $1500 for audio-visual equipment, $15000 for food (75 participants – 1 breakfast, 2 lunches, 1 dinner), $2000 for publishing and advertising.

Evaluation

$8,000 for project evaluation consultant.  These funds will used to cover the following: $6000 for consultant fees for 12 days @ $500/ day.  $2000 for travel reimbursement.

Key Personnel

Edwin Marty, JVUF, Director

Edwin the founder and Chairman of the Board the Jones Valley Urban Farm. He will oversee the whole project as project director.  Mr. Marty will be on the evaluation team at the end of each session. He studied agroecology at the University of California, Santa Cruz, has worked on various agriculture projects around the world, and is currently the assistant garden editor at Southern Living.

Justin Coley, JVUF, farm manger

After graduating from Birmingham’s International Baccalaureate High School, Justin attended Tulane University in New Orleans, where he focused his studies on political science and international development issues, with a regional concentration on Latin America.  After studying abroad, Justin became very interested in the issue of food security and, eventually, the subject of Agroecology.  Upon graduating he began work with a company started by a Tulane professor which specialized in Permaculture, and the recycling of waste products via composting and vermi-composting for sale as soil amendment products, principally for use in organic horticulture.  By the end of the summer, Justin chose to move back to Birmingham, Al, and eventually began work with Jones Valley Urban Farm as Farm Manager, where he has continues to increase my knowledge of Agroecology and Urban Farming.

Jeff DeGraffenried, JVUF, Education Coordinator

Jeff obtained a BS degree in Geology and a MS in Environmental Engineering from the University of Alabama.  His 18 years of environmental consulting experience includes owning and operating a small consultancy (10 years) and international development work (2 years). For the last year and a half Mr. deGraffenried has been working with community groups teaching organic farming and doing community extension.  Currently, he is teaching the "Arts and Science of Agriculture", a collaboration between the Jones Valley Urban Farm (JVUF) and The Alabama School of Fine Arts (ASFA.)

Appendix

Community Advisory Committee

Toni Leeth, Central City Neighborhood Association (205) 527-6919

Deak Rushton, James 1 Rushton Foundation (205) 322-1951

Leigh Laser Collins, YMCA (205) 801-6053

Louise Shufford, Park Place Resident (205) 324-8159

Meredith Carswell-Sheline, In-Town, (205) 501-5630

Robby Melvin, Culinard Institute, (205) 283-5482

Gus Heard-Hughes, Heifer International (205)956-0088

Paulette Van Matre, Magic City Harvest (205)591-FOOD

Dr. Amanda Brown, UAB Dept of Nutrition Sciences (205) 934-7005

Board of Directors

JVUF Brochures and Publicity

PD’s Resume

Job description; Urban Garden Coordinator